## Comments
Document: |  | Cleanup Work Plan Former Farmer's Union Oil, Richey, Montana
Facility |  | Former Farmer's Union Oil - Release 0180, FID: 11-05898, TID: 19762, WPID: 35246
Review Comments from: |  | DEQ Petroleum Tank Cleanup Section
Review Comments from: |  | Dawson County Public Health
Review Comments from: |  | Lydia Blinn - PTRCB
Review Comments from:
Reviewer/ Comment # | Page | Section/ | Comment | A, D, E, FD or X1 | Response | A or D2 Additional Comment | Second Response | A or D2
Paragraph/
Line No.
1 |  | Cover Page, Subject Line | Please update "Cleanup Work Plan" to "Groundwater Monitoring Workplan".
2 | 3 | 2.0 Facility Summary and Current Conditions | In paragraph 3, please add a sentence about the monitoring well (MW-11) being destroyed during UST upgrades in 2015, and there are currently only 11 active monitoring wells on site.
3 | 4 | 4.1 Groundwater Sample Collection and Analysis | In paragraph 2, please add Intrinsic Biodegradation Indicators to sample analysis to be consistent with the proposed budget.
4 | 4 | 4.1 Groundwater Sample Collection and Analysis | Per DEQ Guidance and Low-Flow (Minimal Drawdown) Ground-water Sampling Procedures (Puls and Bercelona, 1996), the depth to water should be routinely measured and recorded during purging. The measuement of groundwater elevation during purging, ideal maximum drawdown, and contingency if maximum drawdown is exceeded should be documented in the Work Plan.
5 | 5 | 4.2 Investigation Derived Waste | "Drill cuttings, excess sample materials, drilling fluids" are not expected wastes from this work plan. Reference to these wastes should be removed, or description of how they will be handled and disposed of should be required. The statement "…disposed of according to all applicable local, state and federal laws .." is inadequate.
6 | 13 | Groundwater Monitoring and Sampling Unit Cost Worksheet | Please update the "total Number of Wells at Site" from 12 to 11 and adjust the "Number of Flud Level Measurements Only" accordingly.
END OF DEQ COMMENTS
1
2
3
END OF DAWSON COUNTY COMMENTS
1
2
3
END OF PTRCB COMMENTS
|  | Footnote 1 | A= agree D=disagree E = explanation FD=needs further discussion X=take exception to
|  | Footnote 2 | A= DEQ agrees D= DEQ disagrees