## Comments
Document: |  | Work Plan for Limited Excavation and In-Situ Remediation WP35083
Release |  | Former McGaffick Service, Release 0656
Review Comments from: |  | Rachel Mindt (RM)
Review Comments from: |  | Reed Miner (REM)
Review Comments from:
Review Comments from:
Reviewer/ Comment # | Page | Section/ | Comment | A, D, E, FD or X1 | AWS Response J. Scott Vosen (JSV); Alan Frohberg (AF) | A or D2
Paragraph/
Line No.
RM/ 1 | 19 | Opportunistical Remedial Excavation | Please explain why you chose 625 SF intervals for excavation base samples, and if you are referencing a guidance document for these soil samples. | E | JSV: The proposed excavation closure criteria are taken from DEQ's June 2016 soil sampling guidance, which stipulates sampling criteria for "small sites, excavation depth 2 feet or less." The anticipated opportunistic excavation area is expected to be primarily in the "middle" of the site, and overall construction excavation sidewalls are expected to be shored with pile materials for worker safety, meaning sidewall samples are unlikely to be available for sampling. AF: The FAQ section of DEQ State Superfund website states under the Sampling for the question: What is an acceptable grid size for confirmation sampling? that a 25 feet by 25 feet grid be used. This is equal to the planned 625 SF sampling intervals for base samples.
RM/ 2 | 23 | Groundwater Monitoring | Remedial injections are mentioned frequently in this section of the work plan, however there is no defined scope of work for what would be injected and how. Further explanation will be needed if remedial injections are a chosen remedial alternative. | E | JSV: Design of the remediation system will be completed as part of Task 5 of this work plan. The preliminary expectation is that 2 phases of remedial injections will be needed, but the specifics will be determined during completion of Task 5. AF: The first phase of injections will be utilized to dispose the treated groundwater effluent from an air stripper by upgradient injection of the clean water into the aquifer, thereby encouraging flow of the contaminated groundwater towards the pumped extraction wells. The second phase of injections will entail supplementing the injected stripped water with biologicals enhancements in the future when the groundwater contaminant concentrations no longer degrade by just the pump and treat method. | RM: Please include this explanation you've provided in a revised version of the work plan. Screening intervals for the proposed remedial injection wells should be considered with respect to the other remediation systems proposed. The screening intervals for injections may affect the efficiency of other proposed remedial systems. Additionally, using one well to implement multiple remedial system designs may affect the efficiency of certain systems, as well.
REM/ 1 | 12 | Task 5 - Remediation System Design | Additional explanation is needed as to why a vapor barrier is considered necessary based on depth to water ("roughly 15 feet below the planned Basement B2 Level floor…" WP page 7), reported concentrations of petroleum, and intended use of the basement level with the inherent vapor sources associated with that usage. | E | AF: LNAPL is currently present on top of groundwater, and per the September 2021 Montana Vapor Intrusion Guide, the vertical separation between the LNAPL and basement floor is less than the preliminary screening criteria for eliminating potential PVI. So, the vapor barrier will be an initial line of defense to prevent PVI and will continue to be a barrier as long-term recovery of the LNAPL is achieved. Additionally, the vapor barrier will prevent inflow of air from above the basement floor to the subslab extraction trenches if the SVE option is implemented (see below).
REM/ 2 | 12 | Task 5 - Remediation System Design | Additional explanation is needed for the proposed SVE system. SVE was not addressed in the Release Closure Plan. Based on the observed concentrations in groundwater and the extent of the proposed excavation, the rationale for SVE needs better explanation as well as the data used or that will be used to determine extraction well spacing, screen intervals, etc. | E | AF: AWS does not know at this time if it will need to implement SVE. This determination will occur after the soil excavation work is completed and basal soil sample results can be evaluated, as well as after initial LNAPL recovery and pump and treat results have been evaluated. Construction of SVE trenches below the vapor barrier will be convenient during the foundation construction, and thus is cost-effective. SVE will be used to address possible residual contaminated soil left behind below the building, as well as to address petroleum impacted soil in the smear zone when the LNAPL recovery and groundwater pumping systems are active. As discussed in Task 5, the SVE trenches will initially be passive but have the ability to be converted to an active vacuum withdrawal system, if needed. Parameters for an active SVE system will be based on future pilot scale testing.
REM/ 3 | 12 | Task 5 - Remediation System Design | Additional explanation is needed for the free product recovery equipment/system. LNAPL conductivity was tested in 2021 and AWS indicated that "Overall, the free product recovery testing results indicate LNAPL recovery efforts should be minimal, at this time." The rationale for free product recovery, the methods that are likely to be used, and the data/decision criteria used to select/desigin product recovery (e.g., well spacing, recovery method, temporary product storage, disposal, etc.). | E | AF: LNAPL has continued to be present in existing wells MW-2 and MW-3. Geotechnical drilling also encountered LNAPL in borehole BH-02, southeast of MW-2 (see WP Figure 2). Thus, LNAPL is expected to infiltrate the planned extraction wells during groundwater withdrawal, because of the water table drawdown imparted by pumping. Total fluids recovery (i.e., both LNAPL and groundwater) by dual-phase extraction would not be efficient given the expected low infilration of LNAPL and groundwater to a well. So, AWS plans to implement a combined LNAPL and groundwater recovery strategy using pnuematic pumps that can be adjusted for low-flow conditions. Final design of the LNAPL recovery system will be completed as part of Task 5.
REM/ 4 | 16 | Task 9 - UST Removal … | Coordinate with DEQ UST section. DEQ database indicates that the material used to inert the UST is "unidentified" on may of the USTs closed in place. If USTs are found to have been improperly closed in place, a permit may be required to remove the tanks and current closure requirements may be applicable. | E | JSV: We have discussed the specifics of this site with Seth Hendrix of DEQ's UST Program, and the assumptions noted in the work plan are based on those conversations. As stated in the work plan, we anticipate needing to obtain a UST closure permit for one (1) of the closed-in-place 8,000-gallon gasoline USTs. Seth is aware that identification of the specific tank at the site during removal activities will likely be infeasible.
REM/ 5 | 18 - 20 | Task 10 - Opportunistic Remedial Excavation | Please provide the criteria that will be used to differentiate the extent of "remedial" excavation versus excavation necessary for redevelopment/construction. What criteria will used to segregate "clean overburden" from "dirty" soil that requires disposal. | E | JSV: Free product at the site has been determined to be a mixture of approximately 80% diesel and 20% gasoline. AWS intends to field screen total VOCs using a PID and heated headspace method (AWS SOP-03). However, since soil impacted primarily by diesel is difficult to screen using this method, AWS will also rely on visual and olfactory observations for field screening of petroleum contaminated soil. The extent of remedial excavation will consist of the volume of segregated soil. This can be clarified in a revision of the work plan.
REM/ 6 | 21 | Task 11 - Soil Boring and New Well Installation | What criteria will be used to determine if drill cuttings are "determined to be petroleum contaminated" and therefore segregated for disposal? | E | JSV: See response to REM/ 5 comment above.
REM/ 7 | 21 | Task 11 - Soil Boring and New Well Installation | 11 wells are proposed to replace the existing 6 monitoring wells. A map of proposed locations and explanation of intent (e.g., source area, down-gradient delineation, remediation, etc) of the proposed wells is needed to evaluate the proposed well network. Work Plan indicates that the final number and location of wells will be based on site conditions. What data will be used and what are the decision criteria that will be used to make those determinations? | E | JSV: Once the new building is constructed, placement of new/additional wells will be extremely difficult/costly. The proposed well locations are intended to provide sufficient coverage for potential eventualities which can't be fully known at this time. As stated in the work plan, the use of various some may need to be modified depending on the project phase. For example, wells inititially inteded for extraction or re-injection will eventually need to be utilized for monitoring. We can update Figure 4 in a revision of the work plan to include labels of initial anticipated intent for each well (see screen shot in cell below, where: U = upgradient; S = source area; D = downgradient; I = injection; M = monitoring; E = extraction).
#VALUE!
REM/ 8 | 21 | Task 11 - Soil Boring and New Well Installation | It appears that 25 foot screen intervals are proposed. Please explain how this screen interval is needed for the intended well purpose. | E | JSV: Well depths may vary slightly across the site, depending on bedrock depths observed in the respective borings. The depths of wells (~ 3,960 ft amsl) was selected to facilitate treatment of the full depth of the aquifer above the diorite bedrock (~3,965 ft amsl), based on aquifer testing completed at the site. The top of the screened interval was selected to ensure it is above the historical average groundwater elevation (~3,979 ft amsl).
REM/ 9 | 24 | Task 14 - Remediation System Installation and Operation | see comments above for Task 5 -Remediation System Design | E | AF: See responses to REM/ 1, REM/ 2, and REM/ 3 comments above. JSV: AWS intends to coordinate closely with DEQ following completion of Task 5. This (and the responses to REM/ 1, REM/ 2, and REM/ 3 above) can be clarified in a revision of the work plan.
REM/ 10 | 27 and Attachment C | Task 15 - Laboratory Analysis | Clarification is needed. Text indicates that EDB will not be analyzed, yet the referenced table in Attachment C indicates that it will be analyzed in all monitoring events. Based on historical DCA data, please consider reducing the analysis of DCA after the initial monitoring event. The number of wells sampled and analytical suite may be reduced following the initial monitoring event. | A, E | JSV: The discussion in the text is correct. EDB was inadvertently left in the GWM analytical table in Attachment C (note the cost estimate excludes EDB analyses). This can be corrected in a revision. AWS agrees with the suggestion for stipulating reduction of DCA in future events and typically takes this approach. We also agree with the recommendation for reduction of wells samples, if warranted, for future events. We can include notes clarifying both in a work plan revision.
END of COMMENTS
|  | Footnote 1 | A= agree D=disagree E = explanation FD=needs further discussion X=take exception to
|  | Footnote 2 | A= agree D=disagree