## Comments
Document: | Limited Remedial Investigation Work Plan
Contract: | Release 1054 Pacific Coast Supply
Review Comments from: |  | DEQ Petroleum Tank Cleanup Section
Review Responses from: |  | WGM Group, Inc (WGM) - Tyler Etzel, July 15, 2026
Review Comments from:
Review Comments from:
Reviewer/ Comment # | Page | Section/ | Comments | A, D, E, FD or X1 | Response | A or D2
Paragraph/
Line No.
1 | 4 | 2.2.1 Soil Vapor Sampling | Per DEQs Vapor Intrusion Guidance: Helium gas is the preferred tracer. Please provide additional info and rationale for using liquid tracer isopropyl alcohol. In addition, if isopropyl alcohol is being used it needs to be analyzed by the lab in order to determine if the sample is reliable. | A | Helium gas and a helium meter will be used as a leak detection method during soil gas sampling. Appendix E Cost Estimate has been modified to reflect this change.
2 | 5 | 2.2.1 Soil Vapor Sampling | Please verify/clarify: when stating vapor samples will be analyzed by VOCs you are referring to VOCs via EPA Method TO-15. In addition, the TO-15 analysis must also include lead scavengers EDB and DCA. | A | This has been modified to indicate that VOCs refers to TO-15 and that the TO-15 analysis will include EDB and DCA in the suite of parameters. Appendix E Cost Estimate has been modified to reflect this change.
3 | 6 | 2.1.2 Analytical Methods | DCA was detected in MW-2 when sampled in May 2023, but below RBSLs. Lead scavenger DCA must be included in the sampling suite for groundwater. | A | This has been modified to indicate that VOCs refers to TO-15 and that, in addition to VPH and EPH, the lead scavenger 1,2-dichloroethane (DCA) will be submitted for analysis in all groundwater samples collected. Appendix E Cost Estimate has been modified to reflect this change.
4 | 6 | 3.0 Schedule and Reporting | DEQ cannot approve this work plan due to it containing language regarding funding obligation in the Schedule Section. DEQ’s work plan approval process is independent from the funding obligation process. Once a work plan is approved by DEQ, work can begin immediately regardless of funding obligation. Please provide a schedule in your work plan and include an end date for when all work will be completed. Please remove all language that references funding obligation from this work plan and resubmit. | A | All references to funding obligations by PTRCB have been removed.
5 | 7 | 4.0 Costs | DEQ cannot approve this work plan due to it containing language regarding funding obligation in the Costs Section. DEQ’s work plan approval process is independent from the funding obligation process. Once a work plan is approved by DEQ, work can begin immediately regardless of funding obligation. Please remove all language that references funding obligation from this work plan and resubmit. | A | All references to funding obligations by PTRCB have been removed.
END OF DEQ COMMENTS
|  | Footnote 1 | A= agree D=disagree E = explanation FD=needs further discussion X=take exception to
|  | Footnote 2 | A= agree D=disagree