## Comments
Document: |  | Air Sparge System Installation & Surface/Groundwater Monitoring Work Plan
Contract: |  | Facilty 15-02459 and 15-10105, Releases 192 and 4155, Work Plans 35156 and 35157
Review Comments from: |  | Reed Miner (REM)
Review Comments from:
Review Comments from:
Review Comments from:
Reviewer/ Comment # | Page | Section/ | Comment | A, D, E, FD or X1 | Response | A or D2
Paragraph/
Line No.
1 | 7 | Scope of Work | The scope of work outlined in Section 3.0 Scope of Work is inconsistent with the recommendations cited in the Site History section (pages 5 and 6). There is no explanation as to why previous recommendations are not being followed.
2 | 8 and 9 | Analytical Analysis Charts | The Fall 2026 chart includes a "Analysis Spring Event" total at the bottom and the Spring 2027 shart includes a "Analysis Fall Event" total at the bottom.
3 | 8 and 9 | Analytical Analysis Charts | MW-1 and MW-19 are included without indication of sampling or depth-to-water measurment. For clarity, please include all monitoring wells in the table, identify ones that have been abandoned, damaged, or if excluded from sampling provide rationale.
4 | 14 | Air Sparge Pilot Study | Vapor points are proposed to complete a vapor monitoring network on 5-foot centers. Additional explanation as to how the proposed 5-foot spacing was determined and how it will help design a potential full-scale system would be helpful.
END of COMMENTS
|  | Footnote 1 | A= agree D=disagree E = explanation FD=needs further discussion X=take exception to
|  | Footnote 2 | A= agree D=disagree