## Comments
Document: |  | Groundwater Monitoring Work Plan Required for the Petroleum Release at the Former GW Sales Bulk Plant, BNSF Right-of-Way
Contract:
Review Comments from: |  | DEQ Petroleum Tank Cleanup Section
Reviewer/ Comment # | Page | Section/ | DEQ Comments | A, D, E, FD or X1 | Response | A or D2
Paragraph/
Line No.
1 | 4 | Task 5 | Please specify when each semi-annual groundwater monitoring event will happen | A | Added to Task 5 | A
2 | 4 | Task 4 & Task 5 | Please include methods for waste disposal of NAPL soaked socks and purge water | A | Comments added to Tasks 4 and 5 and costs added for disposal by MSES. | A
3 | 5 | Task 9 | Please provide additional explanation as to what decisions will be made after each interim data submittal and/or consider revising report submittal frequency to those necessary based on decision points. | A | Comments added to Task 9 | A
4 |  |  | Please include all SOPs for methods and sampling protocols associated with this work plan | A | Added as appendice | A
END of COMMENTS
|  | Footnote 1 | A= agree D=disagree E = explanation FD=needs further discussion X=take exception to
|  | Footnote 2 | A= agree D=disagree