## Comments
Document: | Groundwater and SVE Effluent Monitoring Work Plan
Contract: | Choteau Couny Maintenance Yard, Release 3645, WP 35123
Review Comments from: |  | Rachel Mindt (RCM)
Review Comments from: |  | Reed Miner (REM)
Review Comments from:
Review Comments from:
Reviewer/ Comment # | Page | Section/ | Comments | A, D, E, FD or X1 | Response | A or D2 | Comments | A, D, E, FD or X1 | Response | A or D2
Paragraph/
Line No.
RCM 1 | 1 | Title Page | Please refer to Section 1. Title Page of the Cleanup Work Plan Expectations document, and include the following information in the work plan (Release Number, Work Plan ID, DEQ Facility Number, Responsible Party, etc.) | A | Updated
REM 1 | 5 | Section 4.4 | Given that: water levels in individual wells appear to vary about 2 feet, many site monitoring wells have screen lengths of 10 to 20 feet, excessive screen lengths can dilute groundwater samples; please consider limiting screen length from the proposed 30 feet to that needed to achieve the objects of the investigation. | E | Longer screen intervals allow for a more robust monitoring well in areas that have high groundwater fluctuation, such as this facility. By having a larger screen, the well is less likely to have GW above its screen interval. Groundwater samples are unlikely to be diluted given WET's strict compliance to lowflow sampling. Changed to an expected depth interval of 25 to 45 ft | D | The proposed monitoring well is intended to be a replacement well for MW-8. Excluding the water level measured the day after installation and presumably prior to equilibration, water levels measured between 2004 and 2022 have had depths between 37.39 and 35.03. MW-8 was screened from 33 to 43 feet (10 feet of screen). Please consider modifying the proposed screen length or provide additional information to explain the need to adjust the screen interval in the replacement well by such a large amount. | A
REM 2 | 5 | Section 4.4 | The work plan indicates "The exact screen inteval and total depth will be deterimined in the field based on observed zones of contamination, lithology, and water levels." Please describe the decision criteria, for example how much screen will be located above the observed water table, what is field screening results and/or visual/olfactory observations indicate "contamination," how will lithology influence decisions on screen interval and well depth, etc. | D | I don't wish to codify any process or tie our hands to any particular decision. There are a lot of unknowns that can be introduced in well installation and I need to maintain some flexibility for my team to consult with me to deal with these unforseen circumstances. If you would like I can coordinate a meeting with DEQ prior to construction. I do not want to find myself in a scenario where the screen interval is below the water level. | E | DEQ has not requested specific depths but would like further information on what observations/ measurements would be used to determine the screen interval and well depth in the field. For example: The boring log for MW-8 which is to be replaced has limited field screening data, but the data available shows no detections nor descriptions of odor or staining. What field screening concentrations or observations would be considered "contaminated" to a degree that would warrent screening that interval versus casing it off? How will lithology influence those decisions, etc.? | A
REM 3 | 5 and 6 | Section 4.5 | 1. The SOP indicates that a bailer and impeller pump "may be" moved up and down in the screen and well casing and a surge block "can be" used, but it is not clear that a method of surging is required. Please indicate which if any method of surging will be used to develop the well. 2. If surging is not intended for well development, please indicate the intended pumping rate as well develpment by pumping alone should be done at a rate greater than rates used during sampling or purging (example source: EPA, 1992, Monitoring Well Develpoment Guidelines for Superfund Project Managers). | A | Updated text.
REM 4 | 6 | Section 4.8 | "…drawdown will be also be monitored but are not subject to stabilization criteria." Per the DEQ Contaminated Site Cleanup Bureau Groundwater Sampling Guidance (March 2018), Section 3.1.3 drawdown should not exceed 0.3 feet. Intended maximum drawdown and contingencies for if drawdown exceeds intended maximum drawdown should be explained. | A | Updated text.
REM 5 | 8 and 9 | Section 4.13 | 1. As the scope of work is system operation and monitoring, a Cleanup Report is a better means of capturing the scope of work. Please follow the Cleanup Report format contained in the Montana Cleanup Guidance for Petroleum Releases (DEQ, 2020). Adjustments may be needed to include monitoring well installation. 2. Please note that cumulative data tables as proposed in the work plan is required. The most recent report for activities at the facility did not include cumulative data tables. The work plan proposed cumulative data tables is correct. | A | Updated text.
END of COMMENTS
|  | Footnote 1 | A= agree D=disagree E = explanation FD=needs further discussion X=take exception to
|  | Footnote 2 | A= agree D=disagree