## Comments
Document: |  | Groundwater Monitoring Work Plan WP 35176
Contract: |  | Pelican Oil Bulk Plant, Fac. 56-05861, Release 3799
Review Comments from: |  | Reed Miner (REM)
Review Comments from:
Review Comments from:
Review Comments from:
Reviewer/ Comment # | Page | Section/ | Comments | A, D, E, FD or X1 | Response | A or D2
Paragraph/
Line No.
REM 1 | 3 | Groundwater Monitoring/ Page 3 Bullet 1 | Work Plan (WP) indicates field measurements that will be taken, but does not specifiy when the sample will be taken (e.g., based on volume purged or stabilization of field criteria). Per DEQ "Groundwater Sampling Guidance" dated March 2018, stabilization of field criteria is the prefered method. Please indicate the method that will be used, and if stabilization of field criteria is the basis for when samples will be collected indicate the criteria that will be used (e.g., pH +/- 0.1 units, etc.). | A | Work Plan updated accordingly.
REM 2 | 3 | Groundwater Monitoring/ Page 3 Bullet 1 and 3 | Some of the monitoring wells proposed for sampling have been reported as non-detect or below RBSLs for petroleum constituents for multiple events. DEQ understands that injection of remedial fluids has the potential to change conditions. Please consider the proposed wells for sampling and provide additional explanation/rationale for why the proposed monitoring wells have been selected for monitoring. | A | Work Plan updated accordingly.
REM 3 | 3 | Reporting | The report type has not been specified (e.g. Groundwater Monitoring Report, Interim Data Submittal, etc.). Based on the proposed scope of work and purpose of the work plan, a Groundwater Monitoring Report with an updated release closure plan is likely the best report format. | A | Work Plan updated accordingly.
REM 4 | 3 | Schedule and Costs | Please include an estimated schedule so that the approved work plan duration can accommodate it. | A | Work Plan updated accordingly.
END of COMMENTS
|  | Footnote 1 | A= agree D=disagree E = explanation FD=needs further discussion X=take exception to
|  | Footnote 2 | A= agree D=disagree