## Comments
Document: |  | Supplemental Work Plan dated March 5, 2026 (WP 35162)
Contract:
Review Comments from: |  | Jonathan Love, 3/9/26
Review Comments from:
Review Comments from:
Review Comments from:
Reviewer/ Comment # | Page | Section/ | Comments | A, D, E, FD or X1 | Response | A or D2
Paragraph/
Line No.
1/1 | Cover |  | Add Work Plan 35162. | A | Work Plan ID added to Cover Page
1/2 | 1 | 1 | Since a WP request letter was not sent out, remove sentence stating this SWP was requested by DEQ. Could add language the WP scope was discussed w/DEQ. | A | Changed wording to, "This SWP was requested by the landowner and drafted for the Montana Department of Environmental Quality (DEQ) Contaminated Site Cleanup Bureau."
1/3 | 6 | 3.5 | Will there be a waiting period after the sock is removed before measuring and sampling? | A | "No groundwater sampling will occur within 48 hours of removing an absorbent sock to avoid interference to the water column." added to Section 3.4, and language about using an absorbent sock to remove LNAPL prior to sampling removed from Section 3.5.
1/4 | 6 | 3.5 | GW levels are shallow enough to utlize a peri pump vs baldder pump, which reduces the chances of cross-contamination. | A | Section 3.5 edited to add a peristaltic pump.
1/5 | 6 | 3.5 | Remove Lead analysis. | A | Language added to Section 3.5 to clarify that Lead Scavengers will be sampled in the Spring event, but not in the Fall if exceedances are not present.
1/6 | 9 | 4 | One GW report submittal summarizing both sampling events. | A | Language to Section 4.0 revised.
END of COMMENTS
|  | Footnote 1 | A= agree D=disagree E = explanation FD=needs further discussion X=take exception to
|  | Footnote 2 | A= agree D=disagree