## Comments
Document: |  | Groundwater Monitoring Work Plan 35121
Contract: |  | Fac. 15-02272, Release 4202, Work Plan 35121
Review Comments from: |  | Reed Miner (REM)
Review Comments from:
Review Comments from:
Review Comments from:
Reviewer/ Comment # | Page | Section/ | Comments | A, D, E, FD or X1 | Response | A or D2
Paragraph/
Line No.
REM 1 | Title Page | Facility /Release/ Work Plan line | Work Plan ID in title is correct. Work Plan ID in Facility, Release, Work Plan identifier is incorrect. | A
REM 2 | 4 | Section 2.1 | Section 2.1 indicates that a Remedial Investigation Report was requested. Section 2.3 indicates that a groundwater monitoring report will be prepared. Based on the scope of work a groundwater monitoriing report appears appropriate. | A
REM 3 | 5 | Section 2.2 | Stabilization criteria are not identified. Please include as an attachment WCEC SOPs for low-flow sampling that include stabilization criteria and contigency stabilization criteria are not met. | A
REM 4 | 5 | Section 2.2 | Per Low-Flow Sampling methodology, the depth to water should be measured routinely. Drawdown should be minimized (ideally less than 0.3 feet). Drawdown should be mentioned in the work plan, steps to minimize drawdown, and contingency if less than 0.3 feet cannot be achieved. | A
REM 5 | 5 | Section 2.2 | Method of sump sampling is not indicated. Based on conversations between MDT and consultant, and passed on to DEQ, DEQ understands the intent to empty the sump and collect water that infiltrates. This and other method specific plans should be documented in the work plan. | A
END of COMMENTS
|  | Footnote 1 | A= agree D=disagree E = explanation FD=needs further discussion X=take exception to
|  | Footnote 2 | A= agree D=disagree