## Comments
Document: | Groundwater and Vapor Monitoring Work Plan
Contract: | Release 4368, Former Vogue Cleaners, WP 35120
Review Comments from: |  | Rachel Mindt
Review Comments from: |  | Reed Miner (REM)
Review Comments from:
Review Comments from:
Reviewer/ Comment # | Page | Section/ | Comments | A, D, E, FD or X1 | Response | A or D2
Paragraph/
Line No.
Rachel Mindt | 6 | Soil Vapor Intrusion Sampling (Task 6) | SOP-15E is not attached to the work plan. Please include in Appendix A. | A | Updated
REM/ 1 | 3 | Groundwater Monitoring (Task 4) | "…drawdown will be also be monitored but are not subject to stabilization criteria." Per the DEQ Contaminated Site Cleanup Bureau Groundwater Sampling Guidance (March 2018), Section 3.1.3 drawdown should not exceed 0.3 feet. Intended maximum drawdown and contingencies for if drawdown exceeds intended maximum drawdown should be explained. | A | Text updated to address how drawdown will be kept below 0.3 ft
REM/ 2 | 3 | Groundwater Monitoring (Task 4) | "The oil-water interface probe and bladder pump will be decontaminated between each site…" Please clarify if reusable equipment is to be decontaminated between monitoring wells or between release sites. | D,E | Decontamination process explained in the attached SOPS
REM/ 3 | 2 | Groundwater Monitoring (Task 4) | Please provide rationale for sampling selected wells/piezometers. Historical data suggests that a subset of wells may be appropriate. | E | The point of this work plan is to measure/conditions of the subsurface when the system is not operational. Doing so requires monitoring all of the wells on the facility. Text updated
END of COMMENTS
|  | Footnote 1 | A= agree D=disagree E = explanation FD=needs further discussion X=take exception to
|  | Footnote 2 | A= agree D=disagree