## Comments
Document: |  | Work Plan 35192
Contract: |  | EZ Stop West, Facility: 2501313, Spill: 4412
Review Comments from: |  | Edvard Melesh (EM)
Review Comments from: |  | Reed Miner (REM)
Review Comments from:
Review Comments from:
Reviewer/ Comment # | Page | Section/ | Comments | A, D, E, FD or X1 | Response | A or D2
Paragraph/
Line No.
EM 1 | 9 and 10 | Figure 1 and 2 | Well locations between the two figures do not match, based on a quick streetview look, the locations on figure 1 seem to be more accurate, if the proposed wells are placed at the points on the aerial map photo they might end up too close to existing wells MW-3 and MW-4. Please revise the proposed boring map. |  | Addressed | A
EM 2 | 1 | End of Paragraph 1 | Part of the scope of work includes a Release Closure Plan (RCP), the need for a closure plan will be determined based on the results of the current investigation. Please remove it from the current work plan. |  | RCPs are included in the DEQ guidance requirements for GWM and RI Reports. We will be including this in the report, especially since there will be new information to add to the CSM. | D
REM 1 | 4 | Task 4. Monitoring well installation | 1. Given that the historical data includes only one soil sample greater than 10 feet, the boring logs includes data (lithology and PID) based on cuttings only, consider using a different drilling technique with the ability to recover soil cores. 2. Provide additional explanation as to what data will be observed/measured/recorded for the selected drilling technique (sonic, air-rotary, etc.) and how that data will be used to design remediation (e.g., screen interval for SVE wells, injection interval for "barrier," etc. 3. If air rotary is selected, provide additional description as to how soil samples collected from cuttings forced to the surface with air will be representative. |  | Boland's air rotary drill rig is an ODEX that is able to collect split spoons. We will attempt to collect samples with the split spoon. Sonic and other drilling methods volatilize soil cuttings from heat and friction, and in our opinion does not warrant the additional cost. The Site closure will be assessed on groundwater results as there is no direct contact risk at the Site. Air rotary was used to install the source area wells, and downgradient and cross gradient wells are not likely to have soil results representative of worst case soil impacts for closure assessment. | A
REM 2 | 5 | Task 7: Groundwater Monitoring | 5 of the 7 existing monitoring wells have petroleum constituents reported as non-detect or less than RBSLs for all 4 previous monitoring events. Please consider revising the number of wells that will be sampled and/or provide additional explanation as to the rationale for collecting samples from the monitoring wells selected. |  | The Site has not been sampled in some time and a full round of groundwater is recommended to help with decision making and evidence for the remediation step, especially with comments recent received from the board about sample data in preparation for remedial actions. | D
REM 3 | 5 | Task 8 Laboratory Analysis | EPH screen has not historically exceeded 1,000 ug/L in goundwater. Please provide additional explanation as to the proposed number of EPH samples and estimate as to the number that will be fractionated. |  | Since lab costs are reimbursed directly based on laboratory invoices, we include EPH fractions of 50% of samples. | A
REM 4 | 5 | Task 9 Interim Data Submittal | The purpose of an interim data submittal is to convey information to DEQ to make decisions about data gaps and additional mobilizations within the same work plan. As any additional work will be done under a new work plan, and interim data submittal is not required by DEQ. |  | accepted | A
REM 4 | 5 | Task 11 Monitoring Well Installation and Groundwater Monitoring Report | DEQ does not have a report format for proposed report. Based on the scope of work, a Remedial Investigation Report is recommended. |  | accepted | A
END of COMMENTS
|  | Footnote 1 | A= agree D=disagree E = explanation FD=needs further discussion X=take exception to
|  | Footnote 2 | A= agree D=disagree