## Comments
Document: |  | Groundwater Monitoring Work Plan Required for the Petroleum Release at the Former Peavey CO Richey, dated February 20, 2026
Contract:
Review Comments from: |  | DEQ Petroleum Tank Cleanup Section
Responses from: Ethan Perro (Olympus Technical Services)
Reviewer/ Comment # | Page | Section/ | DEQ Comments | A, D, E, FD or X1 | Response | A or D2
Paragraph/
Line No.
1 |  |  | Please include all format sections and information required in Montana's Groundwater Monitoring Work Plan and Report Guidance for Petroleum Releases | A | Added | A
2 | 3 | Task 4 | Please include SOP for well development as referenced in this paragraph | A | Added as appendice | A
3 | 3 | Task 5 | 1. Please specify when each semi-annual groundwater monitoring event will happen. 2. Please include SOP for GW monitoring and sampling | A | Added to task 5 and added SOP as appendice | A
4 | 4 | Task 9 | Please provide additional explanation as to what decisions will be made after each interim data submittal and/or consider revising report submittal frequency to those necessary based on decision points. | A | Added to task 9 | A
5 |  |  | Please include all SOPs for methods and sampling protocols associated with this work plan | A | Added | A
End of DEQ Comments
|  | Footnote 1 | A= agree D=disagree E = explanation FD=needs further discussion X=take exception to
|  | Footnote 2 | A= agree D=disagree