## Comments
Document: |  | Draft Groundwater Monitoring & Drinking Water Sampling Work Plan 35207
Facility |  | Swan Valley Center - Release 4769, FID: 32-03617, TID: 25306, WPID: 35207
Review Comments from: |  | DEQ Petroleum Tank Cleanup Section
Review Comments from:
Review Comments from:
Review Comments from:
Reviewer/ Comment # | Page | Section/ | Comment | A, D, E, FD or X1 | Response | A or D2 Additional Comment | Second Response | A or D2
Paragraph/
Line No.
1 |  |  | Please include all format sections and required information for Facility History/Release Background as described in DEQs Montana Groundwater Monitoring Work Plan and Report Guidance for Petroleum Releases.
2 | 2 | 2.1 Groundwater Monitoring | Please include SETs SOPs for all methods and sampling protocols associated with this work plan
3 | 3 | 2.2 South Well Sampling | Please include additional information regarding how the South Well will be sampled (i.e. will it be purged, where is the planned sample point, are you going to use a pump etc.)
4 | 3 | 2.2 South Well Sampling | Please provide further details on the timing of each quarterly sampling event (seasonal variations in pumping conditions at the rented cabins and facility usage, seasonal fluctuations in groundwater elevations etc.).
5 | 3 | 2.3 Analytical Summary Table | Please specify if any QA/QC samples will be collected.
6 | 4 | 3.2 Timeline & Costs | DEQ cannot approve this work plan due to it containing language regarding funding obligation in this Section. DEQ’s work plan approval process is independent from the funding obligation process. Once a work plan is approved by DEQ, work can begin immediately regardless of funding obligation. Please provide a schedule in your work plan and include an end date for when all work will be completed. Please remove all language that references funding obligation from this work plan and resubmit.
END OF DEQ COMMENTS
|  | Footnote 1 | A= agree D=disagree E = explanation FD=needs further discussion X=take exception to
|  | Footnote 2 | A= DEQ agrees D= DEQ disagrees