## Comments
Document: |  | Remedial Investigation Work Plan
Contract: |  | Fac. 27-02343, Release 6648, Work Plan 35141
Review Comments from: |  | Reed Miner (REM)
Review Comments from:
Review Comments from:
Review Comments from:
Reviewer/ Comment # | Page | Section/ | Comments | A, D, E, FD or X1 | Response | A or D2
Paragraph/
Line No.
REM 1 | 5 and 6 | Subsurface Investigation | Page 5 first bullet item and page 6 fifth bullet of page: soil samples to be collected from the base of the boring. Please provide additional explanation as to purpose of base of boring sample and under which conditions samples from the base of the boring will be collected. | A, E | The sample collected from the base of the boring will serve to assess the extent of soil contamination to the greatest depth possible. Three samples will be collected for lab analysis from each borehole, one from the soil/groundwater interface, one from the zone of greatest petroleum impact as identified by PID screening, and one from the base of the borehole. A basal soil sample may not be collected if PID readings from that interval show negligible VOC content. This condition will be clarified in this section of the report.
REM 2 | 6 | Subsurface Investigation | 2nd bullet: "...soil borings will be installed using direct-push drilling techniques.." Direct-push is likely inconsistent with intent to install 2-inch diameter monitoring wells and inconsistent with the driller's bids. | A | Soil borings will be installed using hollow-stem auger drilling techniques. Updated to reflect driller's bid.
REM 3 | 6 | Subsurface Investigation | 2nd bullet: "...soil borings will be continually logged to a depth of approximately 30 feet…" Due to the unknown depth to groundwater, it may be possible to stop the boring short of 30 feet under certain conditions. Please also identify the criteria that will be used to determine the total depth of the boring in the field. | A, E | Because depth to groundwater is unknown, PID measurements in the field and observations of soil moisture content will determine the true depth of the borehole. Wells will be drilled to at least 5 feet deeper than the soil/groundwater interface to accommodate the installation of a 10-foot well screen, which may result in a well shallower than 30 feet. This condition will be clarified in this section of the report.
REM 4 | 6 | Subsurface Investigation | 2nd and 3rd bullet: "...soil borings will be continually logged to a depth of approximately 30 feet…" Please confirm intent to collect continuous soil cores for logging. One driller's bid appears to indicate that samples will be collected on 5-foot centers. | A, E | Field samples will be collected continuously from a split-spoon sampler in order to assess lithology and VOC content with a PID, but a maximum of three laboratory samples will be collected at a depth interval representative of observed contamination extent and magnitude, with sample location and interval dependant on field observations. Text will be edited to clarify this. Tetra Tech has clarified with the drilling subcontractor that coring will be continuous to allow observance of the entire soil column.
REM 5 | 6 | Subsurface Investigation | 5th bullet of page: "Up to three soil samples will be collected from each soil boring…" The attached soil sampling SOP describes multiple methods of soil sampling. Please indicate which of the multiple methods will be used and if reusable equipment is used please indicate decontamination method(s). | A, E | Subsurface soil samples will be collected using a split-spoon sampler, as described in section 2.4.1 of the provided soil sampling SOP. Reusable equipment will be used as part of this sampling method and decontamination will occur following the guidelines for drilling and monitoring well installation and borehole soil sampling downhole equipment decontamination as described in sections 2.2 and 2.3 of the providedd general equipment decontamination SOP. Text will be updated to clarify these sampling and decontamination methods. To reduce cross contamination, drilling will commence at the boring with lowest anticipated petroleum impacts and end with the boring with highest anticipated petroleum impacts. Drilling augers and split spoons will be decontaminated thoroughly in accordance with the SOP.
REM 6 | 6 | Subsurface Investigation | 6th bullet of page: It is clear that drill cuttings are to be drummed and sampled, but final disposition and anticipated duration of temporary storage on-site is unclear. | A, E | Drums will be stored onsite in a protected area, until receipt of waste characterization results have been reviewed and approved by an accredited solid waste facility. Drums will be shipped to the solid waste facility as soon as transportation and disposal have been arranged. Text will be updated to include these details.
REM 7 | 6 | Monitoring Well Installation | 1st bullet item: "..well screen … installed from 5' to approximately 15' bgs." This is inconsistent with the depth of about 30 feet. As the depth to first groundwater is unknown, please describe the criteria that will be used to determine the total depth of the boring/well and the screen interval. | A, E | A 10-foot well screen will be installed that is approximately centered at the soil/groundwater interface, with approximately 3 feet of screen isntalled above the first appearance of moisture in the soil column to accommodate for seasonal fluctuation. Text will be updated to remove references to specific depths at which the well screen will be installed and rather describe the spatial relationship to groundwater levels that will be determined in the field.
REM 8 | 7 | Groundwater Monitoring | 3rd bullet: low-flow pumping method is indicated and field parameters are identified; however the SOP provided includes mutiple methods of determining sample collection such as based on well volume and based on stabilization of field parameters. Please indicate what criteria will be used to determine when samples will be collected and contingicies if stablization is not achieved or drawdown exceeds 0.3 feet. | A, E | Samples will be collected based on stabilization of field parameters as defined in Table 1 of the groundwater sampling SOP, if the available well volume allows for this method. Well volume will be calculated prior to sampling to determine whether volume is sufficient to allow for complete parameter stabilization prior to sampling, and if not, the well will be purged of the maximum volume of water while still reserving enough to be sampled. If drawdown exceeds 0.3 feet, then the well will be allowed to recharge prior to sampling. Text will be updated to clarify these conditions.
REM 9 | 8 | Remedial Investigation Report Preparation | Please be advised that data tables are to be cumulative. | A, E | Text will be updated to reflect that data tables will be cumulative and include soil and groundwater analytical data from the previous site investigation.
REM 10 | Cost Estimate Breakdown | Task 13 | IBI Report Modifier, staff scienties (2 events): groundwater monitoring has been proposed for one event and IBIs are not part of the analytical suite. It is unclear if something is missing from the work plan or if there is an error in the cost estimate tasks. | A | This will be removed and must have been a carry over from a previous work plan.
END of COMMENTS
|  | Footnote 1 | A= agree D=disagree E = explanation FD=needs further discussion X=take exception to
|  | Footnote 2 | A= agree D=disagree