## Comments
Document: |  | Corrective Action Plan 35145
Facility |  | Town Pump Inc Eureka FID: 27-08699 Release 6674 Work Plan 35145
Review Comments from: |  | DEQ Petroleum Tank Cleanup Section
Review Comments from:
Review Comments from:
Review Comments from:
Reviewer/ Comment # | Page | Section/ | Comment | A, D, E, FD or X1 | Response | A or D2
Paragraph/
Line No.
1 | 5 | 3.1/4th Paragraph | Based on field screening results, please make sure soil samples are collected in order to fully define the vertical extent and magnitude in each soil boring. This may include more than two soil samples collected in some locations. |  |  | A
2 | 5 | 3.1/5th Paragraph | Please specify if any QA/QC samples will be collected. |  |  | A
3 | 6 | 3.3/1st Paragraph | 1. Please include how long after well development wells will be allowed to equilibrate before first round of GW sampling. 2. Please include how well development purge water will be disposed. |  |  | A
4 | 11 | 5.1/1st Paragraph | 1. Please specify if any QA/QC samples will be collected. 2. In accordance to low-flow sampling methodology the depth to water should be measured routinely. Drawdown should be mentioned in the work plan or WCECs SOP. 3. Please clarify exactly what wells are going to be sampled during each event. The fourth sentence of section 5.1 states only the new wells will be sampled but the analytical analysis chart shows existing wells will also be sampled. |  |  | A
5 | 12 | 5.1/3rd Paragraph | Please clarify what each well will be analyzed for during GWM. This paragraph is different from the analytical analysis chart. |  |  | A
6 | 13 | 6.1/1st Paragraph | 1. Please provide rationale for installing soil vapor probes at only 3 ft. bgs (i.e. will the barometric pressure, temperature, or breakthrough of ambient outdoor air cause issues?) Per DEQ PVI guidance, DEQ recommends that soil vapor probes be deeper than 5 ft bgs unless there is good reason for them to be shallower. 2. Please clarify how each vapor probe will be constructed (i.e. will 10/20 silica sand be used around the perforated tip and then sealed with bentonite?) 3. DEQ recommends soil vapor samples be collected during different times of the year and site conditions such as high and low GW elevations. |  |  | A
7 | 13 | 6.2/1st Paragraph | Per DEQs PVI guidance, in addition to conducting the tracer test using helium, a shut in test should be conducted on the sampling train. |  |  | A
8 | 16 | 8.1 | Please include estimated implementation dates for the planned workflow outlined in this section. |  |  | A
9 | 17 | List of Figures | Please include on a figure the proposed soil vapor probe locations. |  |  | A
END OF DEQ COMMENTS
END of COMMENTS
|  | Footnote 1 | A= agree D=disagree E = explanation FD=needs further discussion X=take exception to
|  | Footnote 2 | A= agree (based on revisions made in revised WP dated 4/1/26) D=disagree