## Sheet1
Document Name / Type: |  | Remedial Investigation, Work Plan 35110
Facility / Property: |  | Former Rambur Construction, 401 N 17th Street, Billings, Yellowstone Co., MT, Montana; FID 00-32594 (TID 32594), Release 6699, Work Plan 35110
Review Comments from: |  | Jay Shearer, DEQ-PTCS, February 17, 2026
Review Comments from: |  | Jonathan Love, DEQ-PTCS, February 23, 2026
Review Comments from: |  | Joe Laudon, RTI
Review Comments from:
Review Comments from:
Reviewer/ Comment # | Page | Section/ | Comments | A, D, E, FD or X1 | Response | A or D2
Paragraph/
Line No.
1/1 | 3 | Scope of Work, 7th bullet point | Recommend this Task includes a description of monitoring that specifies both GWM and PVM events will be conducted at the same time intervals for high and low GW events. | FD | No issue with language about timing of GWM events. Text revised accordingly. PVI investigation was not included in this WP. If initial soil and groundwater data indicate PVI potential, will recommend PVI investigation following soil boring/monitoring well installation and first round of sampling via Form 8.
1/2 | 4 | Soil Borings, 1st paragraph | Recommend sentence "The boreholes will be advanced to the soil-groundwater interface if no impacts are encountered" to include: 'The boreholes will be advanced through the soil-groundwater interface several feet to evaluate possible submerged petroleum smear zone(s)' | A | Text revised accordingly.
1/3 | 4 | Soil Borings, 3rd paragraph | recommend collecting soil samples of petroleum-contaminated soil in Vadose Zone, at groundwater-table, top and base of smear zone. Bottom of hole sample not needed, only PID. Borings should be advanced well beyond base of smear zone. | A | Text revised accordingly.
2/1 | 5 | Groundwater Sampling | Recommend using a peri pump vs the stainless steel submersible pump. Less chance of cross-contamination and gw should be shallow enough for use of peri pump. | A | Text revised accordingly.
2/2 | 6 | Groundwater Sampling | Recommend pump/tubing intake depth should calculated in top 1/3 of water column vs 3-4 feet below water table. | A | Text revised accordingly.
3/1 | 7 | Evaluation and Reporting | Based on recent experience with PTRCB and what they will allow for reporting, recommend Interim Data Submittal after soil boring/well installation and 1st round of sampling with recommendation regarding conducting soil vapor probe installation before 2nd GWM event with PVI sampling to be conducted during second GW sampling event. |  | Text revised accordingly.
3/2 | 8 | Schedule | Schedule changed to 1st GWM event in early summer 2026 (high groundwater) and second GWM event in late fall 2026 (low groundwater. |  | Text revised accordingly.
END of COMMENTS
|  | Footnote 1 | A= agree D=disagree E = explanation FD=needs further discussion X=take exception to