## Comments
Document: |  | Remedial Investigation Work Plan
Facility |  | Madison County Shop - Release 764, FID: 28-02588, TID: 24584, WPID: 35166
Review Comments from: |  | DEQ Petroleum Tank Cleanup Section
Review Comments from: |  | Brandon Kingsbury - Tetra Tech
Review Comments from:
Review Comments from:
Reviewer/ Comment # | Page | Section/ | Comment | A, D, E, FD or X1 | Response | A or D2 Additional Comment | Second Response | A or D2
Paragraph/
Line No.
1 | 4 | Scope or Work | Please clarify the general scope of work. There seems to be contradictory statements regarding exactly how many soil borings and monitoring wells will be installed during this RI. | A, E | Wp revised to indicate that soil borings will all be drilled to 15 feet for 8 total soil borings and 5 monitoring wells. | A
2 | 4 | Subsurface Investigation/Bullet Point 2 | The last sentence regarding sampling protocols is different from following sections; please clarify. | A | Statement on sampling removed. Defer to the description of sampling in bullet 7. | A
3 | 5 | Subsurface Investigation/Bullet Point 4 | Please clarify how deep each soil boring will be advanced. | A, E | Language added that the total depth of each boring will be 15 feet. If contamination is discovered at the terminus, then additional boring will occur. | A
4 | 5 | Subsurface Investigation/ Bullet Point 7 | Please include what PID readings will be considered contaminated soil and information, data, and/or guidance to justify. | A | Added that 50 ppm will be a threshold for assessment. Please note that diesel contamination will be evaluated qualitatively in the field due to low H'. | A
5 | 5 | Subsurface Investigation/ Bullet Point 8 | Please define/clarify what field screening criteria will be used to determine contaminated soil vs. non contaminated soils | A | Text added clarifying criteria for containerizing impacted soils. | A
6 | 5 | Subsurface Investigation | Please specify if any QA/QC samples will be collected. | A | Text added- a duplicate will be collected at a frequency of one duplicate per batch or per every 20 samples. | A
7 | 6 | Monitoring Well Installation/Bullet Point 1 | Same comment as #1. | E | While borings will be advanced to up to 15 feet, monitoring wells will be completed generally between 2 and 12 feet, but may vary to 3 to 13 feet based on water levels which have historically been quite shallow. "approximate" has been used. | A
8 | 6 | Monitoring Well Installation/ Bullet Point 2 | 1. At a minimum, please collect initial clarity/turbidity and final clarity/turbidity measurements. 2. Please include how long after monitoring well development the first groundwater sampling event will occur. | A, E | 1. Added that turbidity measurements will be collected initially and a final reading collected with a goal of at most a turbidity of 20 NTU or best achievable. 2. To allow for equilibration with the aquifer, wells will be allowed to site for at least 24 hours prior to sampling | A
9 | 6 | Groundwater Monitoring | The SOP for GW sampling stability requirements doesn’t match DEQ guidance, specifically ORP stabilization criteria. Please clarify and/or update accordingly. | A, E | SOP remains, but stabilization criteria have been added as table 1 to the WP. | A
10 | 6 | Groundwater Monitoring | Please include what month the seasonally high groundwater monitoring event will occur and rationale for considering this seasonally high groundwater conditions. | A, X | This may be May or June based on the hydrograph at Twin Bridges: Due to timing of this work plan, the high monitoring event may be postponed until May or June of 2027 to correspond to high groundwater conditions as indicated though periodic monitoring of the USGS station along the Jefferson River at Twin Bridges Montana. | A
11 | 6 | Groundwater Monitoring | Please clarify the second sentence in the 4th bullet point. | A | The text has been changed to read: One groundwater sample will be collected from each monitoring well and one QA/QC field duplicate sample will be collected for each of the two groundwater monitoring events. All groundwater samples will be analyzed for Massachusetts method VPH and EPH. In accordance with DEQ guidance, if the EPH concentration in water exceeds 1,000 micrograms per liter (µg/L), then an EPH fractionation analysis is required (MTDEQ, 2024). For cost estimating purposes it is assumed that eight water samples will be analyzed for EPH fractions, including four samples per event. | A
12 | 7 | Vapor Sampling | 1. Please include all the installation, sampling criteria, and leak detection tests as described in the RI work plan for the Town Station in Gardiner. 2. Please include how many vapor sampling events will be conducted and when. 3. Please confirm/specify, will SB-02-26 only be advanced to 4 to 5 ft Bgs or will it be advanced like the other soil borings to assess any other potential receptors in the source area? 4. "The vapor probe will only be completed if conditions are viable for sampling of soil vapor in accordance with DEQ's vapor intrusion guide". Please include what these specific conditions are in the work plan. 5. Please include if soil vapor samples will be analyzed by method APH and if lead scavengers will be included. 6. Please provide rationale for installing soil vapor probes at only 4 ft. Bgs (i.e. will the barometric pressure, temperature, or breakthrough of ambient outdoor air cause issues?) Per DEQ PVI guidance, DEQ recommends that soil vapor probes be deeper than 5 ft Bgs unless there is good reason for them to be shallower. | A, E | Text added detailing vapor probe sampling and leak detection details. Text added to discuss that the vapor prob e boring will be utilized for the subsurface assessment to a full 15 feet bgs. Explanation that really shallow groundwater may prevent the soil vapor probe from being completed deeper than 4 feet but an attempt to do so will be made. | A
13 | 8 | Schedule and Budget | DEQ cannot approve this work plan due to it containing language regarding funding obligation in the Schedule Section. DEQ’s work plan approval process is independent from the funding obligation process. Once a work plan is approved by DEQ, work can begin immediately regardless of funding obligation. Please provide a schedule in your work plan and include an end date for when all work will be completed. Please remove all language that references funding obligation from this work plan and resubmit. | A | Funding removed. Schedule added. | A
14 |  | Figure 4 | In addition to the proposed soil boring and well locations, DEQ recommends including a soil boring and/or well on the north side of the former UST basin. | X | Boring location added just north of UST basin. | A
END OF DEQ COMMENTS
|  | Footnote 1 | A= agree D=disagree E = explanation FD=needs further discussion X=take exception to
|  | Footnote 2 | DEQ A= agree DEQ D=disagree