## Guide
Site ID # | Primary Heading | Site Name & Title or Subject | Date | Author
MDT Maintenance Facility, Helena Fairgrounds
Unofficial Site File Index
1 | Ranking Sheet and Database Forms
2 | Public Participation/Information Requests/Media
3 | Miscellaneous Correspondence
4 | Site Summaries (various notes from different dates)
5 | Underground Storage Tank Files Information
6 | Site Identification (1988)
7 | Phase I through III Preliminary Site Investigation (July 1988 to August 1988)
8 | Remedial Investigation Review Report (GeoResearch, 1/92)
9 | Post RI Additional Sampling Requirements, Work Plan and Summary Report (January 1997
10 | Additional Monitoring Well Installation and Soil/Groundwater Sampling (October 1994 to January 1996)
11 | VCRA Guidance Letters (DEQ)
12 | Environmental Site Assessment, Helena Fairgrounds and Ryan Fields (Maxim, 1997)
13 | Pre-VCRA Application Coordination/Additional Sampling (2001)
14 | Voluntary Cleanup Plan (5/02) |  | 2002-05-01
15 | Supplemental Investigation
15 | Supplemental Investigation | DEQ letter to MDT re: Additional sampling requirements | 2005-07-06 | DEQ
15 | Supplemental Investigation | DEQ field inspection report | 2005-08-25 | DEQ
15 | Supplemental Investigation | Laboratory report re: August 2005 test pit soil sample results | 2005-09-13
15 | Supplemental Investigation | DEQ Memo re: Suspect petroleum release | 2005-10-20 | DEQ
15 | Supplemental Investigation | DEQ internal Memo re: Arsenic background concentrations in groundwater | 2005-12-02 | DEQ internal
15 | Supplemental Investigation | MDT letter to DEQ re: MDT response to DEQ memo dated 12/2/2005 | 2006-03-15 | MDT
15 | Supplemental Investigation | Phone log DEQ to MDT re: Dissolved iron analysis | 2006-04-12 | DEQ
15 | Supplemental Investigation | MDT sampling report re: July 2005 results
15 | Supplemental Investigation | Cover page re: MDT report May 2006 sampling results and petition for closure | 2006-08-28 | MDT
15 | Supplemental Investigation | May 2006 GW Monitoring Report | 2006-08-28 | MDT
15 | Supplemental Investigation | Email message re: DEQ receipt of May 2006 sampling results | 2006-09-08 | DEQ
15 | Supplemental Investigation | DEQ internal meeting notes: response to MDT petition for closure | 2007-01-04 | DEQ internal
15 | Supplemental Investigation | File memo re: DEQ/MDT meeting notes | 2007-01-19 | DEQ
15 | Supplemental Investigation | DEQ letter to MDT re: regulatory oversight issues | 2007-01-24 | DEQ
15 | Supplemental Investigation | Email correspondence re: additional investigation guidance | 2007-02-01
15 | Supplemental Investigation | Email correspondence re: proposed groundwater monitoring well | 2007-02-26
15 | Supplemental Investigation | Email correspondence re: monitoring well requirements for MW-17 | 2007-05-04
15 | Supplemental Investigation | Email correspondence re: MW-20 sampling schedule and analysis | 2007-06-11
15 | Supplemental Investigation | Phone log DEQ to MDT re: MW-20 groundwater results | 2007-06-11 | DEQ
15 | Supplemental Investigation | Email correspondence re: MDT meeting request | 2007-09-10
15 | Supplemental Investigation | Phone log DEQ to MDT re: quarterly groundwater monitoring notification | 2007-09-11 | DEQ
15 | Supplemental Investigation | Phone log DEQ to MDT re: meeting schedule | 2007-09-27 | DEQ
15 | Supplemental Investigation | Cover Page: October 2007 groundwater monitoring report | 2007-10-29
15 | Supplemental Investigation | Cover Letter: October 2007 groundwater monitoring report | 2007-10-30
15 | Supplemental Investigation | Email correspondence re: meeting schedule (11/2/2007) | 2007-11-02
15 | Supplemental Investigation | Email correspondence re: DEQ report review comments and MDT response | 2007-11-05
15 | Supplemental Investigation | Final Revised GW Monitoring Report | 2008-01-07 | MDT
15 | Supplemental Investigation | File memo: DEQ internal meeting notes | 2008-01-28 | DEQ internal
15 | Supplemental Investigation | Phone log MDT to DEQ re: discuss outcome of DEQ internal meeting | 2008-02-01 | MDT
15 | Supplemental Investigation | Phone log DEQ to Tetra Tech re: Phase I ESA notification | 2008-02-14 | DEQ
15 | Supplemental Investigation | MDT groundwater monitoring report | 2008-06-06 | MDT
15 | Supplemental Investigation | File memo: DEQ internal meeting notes | 2008-06-23 | DEQ internal
15 | Supplemental Investigation | DEQ internal meeting notes | 2008-06-23 | DEQ internal
15 | Supplemental Investigation | Phone log DEQ to MDT re: DEQ can provide closure but cannot delist the facility | 2008-06-30 | DEQ
15 | Supplemental Investigation | Email correspondence re: DEQ site closure and delisting rationale | 2008-07-09
15 | Supplemental Investigation | Phone log DEQ to Olympus re: ERCLs and VCP submittal | 2008-10-24 | DEQ
15 | Supplemental Investigation | DEQ internal meeting notes re: closure options | 2008-10-29 | DEQ
15 | Supplemental Investigation | DEQ letter to MDT re: closure guidance letter | 2008-11-07 | DEQ
15 | Supplemental Investigation | Voluntary Cleanup Plan for Soil Portion of the Facility | 2008-12-05 | Olympus
15 | Supplemental Investigation | Voluntary Cleanup Plan cover letter | 2008-12-10 | Olympus
15 | Supplemental Investigation | Water Quality Protection Division Voluntary Cleanup Plan comments | 2008-12-30
15 | Supplemental Investigation | DEQ Voluntary Cleanup Plan comments | 2009-01-09 | DEQ
15 | Supplemental Investigation | DEQ/MDT meeting notes | 2009-03-25
15 | Supplemental Investigation | MDT questions regarding DEQ comments | 2009-03-25 | MDT
15 | Supplemental Investigation | MDT Rail Spur sampling and analysis plan | 2009-03-26 | MDT
15 | Supplemental Investigation | Email correspondence re: DEQ review of MDT Rail Spur sampling and analysis plan | 2009-04-01 | DEQ
15 | Supplemental Investigation | Email correspondence Olympus to DEQ re: Herbicide analysis problem | 2009-05-26 | Olympus
15 | Supplemental Investigation | Phone log Olympus to DEQ re: analytical problems with surface soil samples | 2009-05-26 | Olympus
15 | Supplemental Investigation | DEQ internal meeting notes | 2009-06-04 | DEQ
15 | Supplemental Investigation | Email correspondence Olympus to DEQ re: Rail spur investigation results | 2009-06-11 | Olympus
15 | Supplemental Investigation | Email correspondence Olympus to DEQ re: Rail spur investigation results | 2009-06-11 | Olympus
15 | Supplemental Investigation | DEQ/Seyler email re: DEQ VCRA webpage updated re: Important changes to the VCRA Statute | 2009-06-11 | DEQ/Seyler
15 | Supplemental Investigation | DEQ/MDT meeting notes | 2009-06-11
15 | Supplemental Investigation | Draft Surface Soil Sampling and Analysis Plan | 2009-06-12 | MDT
15 | Supplemental Investigation | Revised sample location map | 2009-06-15
15 | Supplemental Investigation | Email correspondence Olympus to DEQ re: DEQ review of MDT draft surface soil sampling and analysis plan | 2009-06-15 | Olympus
15 | Supplemental Investigation | File memo re: Follow-up to MDT/DEQ meeting | 2009-06-19
15 | Supplemental Investigation | Phone log Olympus to DEQ re: Preliminary soil investigation results | 2009-07-09 | Olympus
15 | Supplemental Investigation | MDT surface soil investigation report | 2009-07-09 | MDT
15 | Supplemental Investigation | DEQ internal meeting notes | 2009-07-09 | DEQ
15 | Supplemental Investigation | DEQ/MDT meeting notes | 2009-07-10
15 | Supplemental Investigation | DEQ internal meeting notes | 2009-07-13 | DEQ
15 | Supplemental Investigation | Email correspondence DEQ to Olympus re: MDT response language to DEQ comment number 53 | 2009-07-24 | DEQ
15 | Supplemental Investigation | DEQ/MDT meeting notes | 2009-07-29
15 | Supplemental Investigation | DEQ/L&C Co. Water Quality Protection District meeting notes | 2009-07-29
15 | Supplemental Investigation | Document Submittal: Revised VCP dated July 30, 2009 | 2009-07-30
15 | Supplemental Investigation | File memo re: technical review summary of the July 2009 VCP | 2009-08-06 | DEQ
15 | Supplemental Investigation | Lewis & Clark County VCP review results | 2009-08-07 | L&C County
15 | Supplemental Investigation | DEQ comments on the revised VCP dated July 30, 2009 | 2009-08-20 | DEQ
15 | Supplemental Investigation | Phone log DNRC to DEQ re: status of DNRC floodplain maps | 2009-08-20 | DNRC
15 | Supplemental Investigation | Cover letter re: revised VCP dated August 24, 2009 | 2009-08-24
15 | Supplemental Investigation | Cover letter re: revised VCP dated August 27, 2009 | 2009-08-27
15 | Supplemental Investigation | DEQ comments on the revised VCP dated August 24, 2009 | 2009-08-27 | DEQ
15 | Supplemental Investigation | Email correspondence Olympus to DEQ re: final VCP revisions | 2009-08-28 | Olympus
15 | Supplemental Investigation | Completeness letter: DEQ has determined the VCP dated August 27, 2009 is complete | 2009-08-30 | DEQ
15 | Supplemental Investigation | Legal ad submittal the Helena Independent record | 2009-08-31
15 | Supplemental Investigation | Legal ad printed in the Helena Independent record | 2009-09-02
15 | Supplemental Investigation | Legal ad printed in the Queen City News | 2009-09-02
15 | Supplemental Investigation | Legal ad certificate of publication | 2009-09-02
15 | Supplemental Investigation | DEQ comments on the VCP dated August 27, 2009 | 2009-09-23 | DEQ
15 | Supplemental Investigation | Email correspondence DEQ to Olympus re: clarification of DEQ comments on the MDT VCP dated August 27, 2009 | 2009-09-24 | DEQ
15 | Supplemental Investigation | Olympus cover letter: replacement pages for the revised VCP dated August 27, 2009 | 2009-09-25 | Olympus
15 | Supplemental Investigation | MDT VCP for the Soil Portion of the Facility | 2009-09-25 | MDT
15 | Supplemental Investigation | VCP responsiveness summary | 2009-09-30
15 | Supplemental Investigation | Email correspondence DEQ to MDT re: DEQ has approved the VCP dated September 25, 2009 | 2009-10-01 | DEQ
15 | Supplemental Investigation | Public Notice request: DEQ submits public notice legal advertisement to the Helena Independent Record | 2009-10-01
15 | Supplemental Investigation | Public notice posting on DEQ website | 2009-10-01 | DEQ
15 | Supplemental Investigation | DEQ letter to MDT re: DEQ provides approval of the VCP dated September 25, 2009 | 2009-10-01 | DEQ
15 | Supplemental Investigation | VCP Approval Legal Advertisement | 2009-10-04
15 | Supplemental Investigation | Email correspondence DEQ to MDT re: DEQ provides MDT with advice filing restrictive covenants | 2009-10-07 | DEQ
15 | Supplemental Investigation | Email message – DEQ to MDT re: DEQ reminds MDT to submit construction completion report as required | 2009-10-29 | DEQ
15 | Supplemental Investigation | Email correspondence MDT to DEQ re: MDT provides an update regarding the placement of institutional controls at the facility | 2011-04-06 | MDT
15 | Supplemental Investigation | Signed Declaration of Restrictive Covenants on Real Property | 2011-06-28
15 | Supplemental Investigation | Draft Construction Completion Report (letter report) | 2012-01-04 | Olympus
15 | Supplemental Investigation | DEQ/Hanson letter to MDT/ Goodman re: Reminder letter to submit a construction completion report | 2012-10-15 | DEQ/Hanson
15 | Supplemental Investigation | DEQ/Hanson & MDT/ Goodman emails re: MDT Request for extension of the CCR due date & DEQ approval | 2012-11-16
15 | Supplemental Investigation | DEQ/Hanson & Olympus/Stein emails re: Preparation of the Construction Completion Report | 2012-12-03
15 | Supplemental Investigation | ** DEQ legal/Brooks & Hanson internal emails re: Legal review of Construction Completion Report | 2013-02-13 | DEQ internal
15 | Supplemental Investigation | DEQ letter to MDT re: DEQ comments re: Construction Completion Report | 2013-02-28 | DEQ/ Hanson
15 | Supplemental Investigation | Declaration of Restrictive Covenants on Real Property | 2013-09-16 | L&C County
15 | Supplemental Investigation | DEQ letter to MDT re: MDT submittal of IC without CCR | 2013-09-30 | DEQ/ Seyler
15 | Supplemental Investigation | Olympus submittal - Construction Completion Report (6/30/14) | 2014-07-02 | Olympus
15 | Supplemental Investigation | DEQ internal email re: Internal status update to C.B & D.M. for 6/30/2014 CCR | 2014-07-02 | DEQ internal
15 | Supplemental Investigation | Draft revised Construction Completion Report | 2014-07-18 | Olympus
15 | Supplemental Investigation | MDT/DEQ email re: MDT's request that DEQ not review the 6/30/14 CCR | 2014-08-07 | MDT/ Goodman
15 | Supplemental Investigation | Olympus submittal - Construction Completion Report (7/31/2014) | 2014-08-07 | Olympus
15 | Supplemental Investigation | MDT/DEQ email re: MDT's request that DEQ not review the 6/30/14 CCR | 2014-08-07 | MDT/ Goodman
15 | Supplemental Investigation | DEQ letter to MDT - No Further Action for CCR & Soils Portion on VCP | 2014-08-19 | DEQ/ Hammer
15 | Supplemental Investigation | State of MT to Lewis & Clark Co - Copy of Grant Deed to State Land - Oct. 31, 2013 | 2014-08-28 | State of MT